## KPI Register
KPI ID | KPI Name | Domain | Subdomain | Definition | Formula | Unit | Direction | Target | Green Threshold | Amber Threshold | Red Threshold | Frequency | Owner | Data Source | Escalation Trigger | Corrective Action Owner | Reporting Pack | Actual (Current) | Status | Variance | Notes | Last Updated
T-01 | PM On-Time Completion Rate | Technical | Preventive Maintenance | Timely completion of scheduled preventive maintenance work orders. | Completed PM on time ÷ Total scheduled PM × 100 | % | Higher | 95% | 95 | 90 | 80 | Weekly | Project Manager | UPKEEP (PM REPORT) | <95% weekly or downward trend 2 weeks | Project Manager | Monthly Dashboard |  |  |  | Contract AQL: ≥95% on-time PM.
T-02 | Weekly Inspection Completion Rate | Technical | Inspections | Timely completion of weekly inspections per plan/AQL. | Completed weekly inspections ÷ Planned weekly inspections × 100 | % | Higher | 95% | 95 | 90 | 80 | Weekly | Project Manager | UPKEEP (RI REPORT) | <95% in any week | Project Manager | Weekly Ops Review |  |  |  | AQL includes ≥95% weekly inspections.
T-03 | Monthly Asset Inspection Coverage | Technical | Inspections | All in-scope assets inspected monthly (coverage). | Assets inspected in month ÷ Total in-scope assets × 100 | % | Higher | 100% | 100 | 98 | 0 | Monthly | Project Manager | UPKEEP (RI REPORT) | <100% coverage | Project Manager | Monthly Inspection Pack |  |  |  | PWS requires monthly inspection of all items.
T-04 | Emergency Response (≤24h) | Technical | Corrective Maintenance | Urgent calls responded to within 24 hours (unless access denied). | Urgent calls responded ≤24h ÷ Total urgent calls × 100 | % | Higher | 100% | 100 | 95 | 0 | Weekly | Project Manager | Call log | Any miss without access-denial justification | Program Manager | Monthly Dashboard |  |  |  | AQL: 100% urgent calls within 24h.
T-06 | CM Backlog Aging (Avg Days) | Technical | Corrective Maintenance | Average age of open CM work orders (days). | AVERAGE(days open for all open CM WO) | Days | Lower | ≤15 (routine) | 15 | 25 | 30 | Weekly | Project Manager | CMMS backlog report | Any emergency WO >2 days; urgent >7 days; routine >30 days | Project Manager | Weekly Ops Review |  |  |  | Also track by priority class.
T-07 | Critical Asset Availability | Technical | Reliability | Operational availability of critical assets/systems. | Operational critical assets ÷ Total critical assets × 100 | % | Higher | 98% | 98 | 95 | 0 | Weekly | Project Manager | Inspection findings / CMMS asset status | <95% for any week | Program Manager | Monthly Dashboard |  |  |  | Define critical asset list in asset register.
T-08 | Repeat Failure Rate (30d) | Technical | Reliability | Repeat failures on same asset within 30 days. | Repeat failures within 30d ÷ Total failures × 100 | % | Lower | <10% | 10 | 15 | 9999 | Monthly | Project Manager | CMMS asset history | >15% or increasing trend 2 months | Program Manager | Monthly Reliability Review |  |  |  | Trigger RCA for top repeat assets.
T-09 | Planned vs Unplanned Work Ratio | Technical | Maintenance Strategy | Share of planned work (PM+RI) vs all work orders. | Planned WO (PM+RI) ÷ Total WO × 100 | % | Higher | 90% | 90 | 80 | 70 | Monthly | Program Manager | UPKEEP analytics | <60% | Program Manager | Monthly Dashboard |  |  |  | Indicator of proactive maintenance maturity.
T-10 | Weekly Look-Ahead Schedule Adherence | Technical | Planning | Execution of planned activities from weekly look-ahead. | Completed planned activities ÷ Total planned activities × 100 | % | Higher | 90% | 90 | 80 | 0 | Weekly | Project Manager | Weekly look-ahead vs actual report | <80% | Program Manager | Weekly Planning Review |  |  |  | Used for access and disruption management.
F-01 | Budget Utilization (Overall) | Financial | Cost Control | Spending versus approved budget for period. | Actual spend ÷ Approved budget × 100 | % | Lower | ≤100% | 100 | 105 | 9999 | Monthly | Program Manager | Cost report / finance tracker | >105% or burn rate anomaly | Program Manager | Monthly Financial Pack |  |  |  | Track also by CLIN.
F-02 | Cost Variance by CLIN | Financial | Cost Control | Variance of actual cost vs budget by contract line item. | Actual CLIN cost − Budgeted CLIN cost | Currency | N/A | Within tolerance |  |  |  | Monthly | Program Manager | Cost tracker by CLIN | Variance beyond tolerance or NTE risk | Program Manager | Monthly Financial Pack |  |  |  | Set tolerances per CLIN and phase.
F-03 | Forecast Accuracy | Financial | Forecasting | Accuracy of cost forecasts vs actuals. | ¦Forecast − Actual¦ ÷ Actual × 100 | % | Lower | ≤10% | 10 | 15 | 9999 | Monthly | Program Manager | Forecast vs actual report | >15% | Program Manager | Monthly Financial Pack |  |  |  | Aim ±5–10% once stable.
F-04 | CM Cost per Work Order | Financial | Corrective Cost | Average corrective maintenance cost per CM work order. | Total CM cost ÷ Number of CM WO | Currency | N/A | Trend |  |  |  | Monthly | Program Manager | CM cost log / CMMS | Sudden spike vs 3-month average | Program Manager | Monthly Financial Pack |  |  |  | Use to detect abnormal repairs.
F-05 | Procurement Lead Time | Financial | Procurement | Time from request to receipt for parts/materials. | Receipt date − request date (days) | Days | Lower | By category |  |  |  | Monthly | Procurement Lead | PO log / inventory receipts | Lead time impacting SLA / downtime | Project Manager | Supply Chain Pack |  |  |  | Track critical parts separately.
F-06 | Invoice Submission Timeliness | Financial | Invoicing | Invoices submitted on time per payment workflow. | Invoices submitted on time ÷ Total invoices due × 100 | % | Higher | 100% | 100 | 95 | 0 | Monthly | Program Manager | Invoice register / WAWF tracking | <95% | Program Manager | Monthly Financial Pack |  |  |  | Ensure documentation package completeness.
C-01 | Client Satisfaction Score | Client | Satisfaction | Average COR/end-user satisfaction score (survey). | Average rating (1–5) | Score | Higher | ≥4.0 | 4 | 3.5 | 0 | Monthly | Program Manager | Survey / meeting feedback | <3.5 | Program Manager | Monthly Dashboard |  |  |  | Use consistent survey questions.
C-02 | Complaint Rate | Client | Service | Number of client complaints received per month. | Count of complaints | Count | Lower | Trend |  |  |  | Monthly | Program Manager | Complaint register | Increasing trend 2 months | Project Manager | Client Service Pack |  |  |  | Segment by category (response, quality, access).
C-03 | Complaint Closure Time | Client | Service | Average days to close client complaints. | AVERAGE(close date − open date) | Days | Lower | By priority |  |  |  | Monthly | Project Manager | Complaint/action log | Overdue complaints | Project Manager | Client Service Pack |  |  |  | Tie to corrective action tracker.
C-04 | Action Item Closure Rate (Client Meetings) | Client | Governance | Closure rate for actions from COR/client meetings. | Closed actions ÷ Total actions × 100 | % | Higher | 90% | 90 | 80 | 0 | Monthly | Program Manager | MoM action tracker | <80% | Program Manager | Governance Pack |  |  |  | Ensure single action owner and due date.
P-01 | Monthly Inspection Report Timeliness | Compliance | Reporting | Monthly inspection report submitted within required window. | Reports on time ÷ Reports due × 100 | % | Higher | ≥90% | 90 | 80 | 0 | Monthly | Program Manager | Transmittal register | <90% | Program Manager | Monthly Compliance Pack |  |  |  | Contract AQL includes ≥90% on-time monthly inspection reports.
P-02 | Procedure / Method / AHA Compliance | Compliance | Procedures | Work executed only with approved procedures / AHA when applicable. | Compliant work packages ÷ Sampled work packages × 100 | % | Higher | 100% | 100 | 95 | 0 | Monthly | QC Engineer | QC audits / field verification | Any non-compliant high-risk work | Program Manager | Monthly Compliance Pack |  |  |  | Maintain traceable approvals and records.
P-03 | Documentation Completeness | Compliance | Documentation | Work orders and deliverables have complete documentation (photos, checklists, approvals). | Complete files ÷ Files reviewed × 100 | % | Higher | 98% | 98 | 95 | 0 | Monthly | CMMS Admin | CMMS audit / file review | <95% | Project Manager | Monthly Compliance Pack |  |  |  | Key for audit defensibility.
Q-01 | First-Time Quality Pass Rate | Quality | Work Quality | Work accepted without rework upon inspection. | Accepted first time ÷ Total inspected × 100 | % | Higher | 95% | 95 | 90 | 0 | Monthly | QC Engineer | Inspection records / NCR log | <90% | Project Manager | Quality Pack |  |  |  | Use with Rework Rate.
Q-02 | Rework Rate | Quality | Work Quality | Percent of jobs requiring rework. | Reworked jobs ÷ Total jobs × 100 | % | Lower | ≤5% | 5 | 8 | 9999 | Monthly | QC Engineer | NCR / rework log | >8% | Project Manager | Quality Pack |  |  |  | Investigate repeat causes.
Q-03 | Audit Compliance Score | Quality | Audit | Share of audit items compliant. | Compliant audit items ÷ Total audit items × 100 | % | Higher | 95% | 95 | 90 | 0 | Quarterly | QC Engineer | Audit checklist | <90% | Program Manager | Quarterly Compliance Review |  |  |  | Align with QCP audit schedule.
Q-04 | NCR Closure Timeliness | Quality | Nonconformance | NCRs closed within agreed due date. | NCR closed on time ÷ Total NCR × 100 | % | Higher | 90% | 90 | 80 | 0 | Monthly | QC Engineer | NCR tracker | <80% or any critical NCR overdue | Program Manager | Quality Pack |  |  |  | Escalate overdue critical NCRs immediately.
Q-05 | Subcontractor Quality Score | Quality | Subcontractors | Compliance score for subcontractor work based on inspections/audits. | Compliant subcontractor inspections ÷ Total subcontractor inspections × 100 | % | Higher | 95% | 95 | 90 | 0 | Monthly | QC Engineer | Subcontractor QC log | <90% | Project Manager | Quality Pack |  |  |  | Tie to subcontractor corrective actions.
S-01 | HSE Corrective Action Closure Rate | HSE | Corrective Actions | HSE actions closed within due date. | Closed on time ÷ Total HSE actions × 100 | % | Higher | 90% | 90 | 80 | 0 | Weekly | Safety Officer | HSE action log | <80% or any high-risk overdue | Program Manager | HSE Pack |  |  |  | Program manager oversight required.
S-02 | Safety Inspection Completion Rate | HSE | Inspections | Completion of planned safety inspections. | Completed inspections ÷ Planned inspections × 100 | % | Higher | 100% | 100 | 95 | 0 | Weekly | Safety Officer | Safety inspection register | <95% | Program Manager | HSE Pack |  |  |  | Zero tolerance for missed planned inspections.
S-03 | Incident / Recordable Count | HSE | Incidents | Count of incidents/recordables in period. | Number of incidents | Count | Lower | 0 | 0 | 1 | 9999 | Monthly | Safety Officer | Incident log | Any recordable incident | Program Manager | Monthly Dashboard |  |  |  | Use also near-miss reporting for leading indicators.
S-04 | Near Miss Reporting Rate | HSE | Leading Indicators | Near misses reported per period (culture indicator). | Number of near misses (or per man-hours) | Count | N/A | Monitor |  |  |  | Monthly | Safety Officer | Near-miss log | Sudden unexplained drop to zero | Program Manager | HSE Pack |  |  |  | Healthy reporting may rise initially.
M-01 | WO Data Quality | CMMS | Data Discipline | Work orders with complete mandatory fields and attachments. | WO complete ÷ WO reviewed × 100 | % | Higher | 98% | 98 | 95 | 0 | Weekly | CMMS Admin | CMMS audit report | <95% | Project Manager | CMMS Pack |  |  |  | Include photos, checklists, time, parts, closure notes.
M-02 | Inventory Accuracy | CMMS | Inventory | Accuracy between physical inventory and CMMS records. | Matching items ÷ Items checked × 100 | % | Higher | 98% | 98 | 95 | 0 | Monthly | Storekeeper | Cycle count vs CMMS | <95% | Program Manager | Supply Chain Pack |  |  |  | Critical for parts availability and audit.
M-03 | Stockout Rate (Critical Parts) | CMMS | Inventory | Stockouts impacting critical work orders. | Stockout events ÷ Critical material requests × 100 | % | Lower | 0% | 0 | 2 | 9999 | Monthly | Storekeeper | WO delay log / inventory log | Any critical stockout | Program Manager | Supply Chain Pack |  |  |  | Prioritize critical system spares.
G-01 | Governance Action Closure Rate | Governance | Program Control | Closure of actions from governance meetings and internal reviews. | Closed actions ÷ Total actions × 100 | % | Higher | 90% | 90 | 80 | 0 | Weekly | Program Manager | MoM action register | <80% | Program Manager | Governance Pack |  |  |  | Supports traceability and accountability.

## Lists
Domain
Technical
Financial
Client
Compliance
Quality
HSE
CMMS
Governance
Direction
Higher
Lower
N/A
Frequency
Daily
Weekly
Monthly
Quarterly
Annual
Owner
Program Manager
Project Manager
Site Engineer
QC Engineer
Safety Officer
CMMS Admin
Storekeeper
Procurement Lead
Reporting Pack
Monthly Dashboard
Weekly Ops Review
Monthly Inspection Pack
Monthly Financial Pack
Quality Pack
HSE Pack
Supply Chain Pack
CMMS Pack
Governance Pack
Client Service Pack
Monthly Reliability Review
Quarterly Compliance Review